## Pivot View (hidden)
Row Labels | Sum of Estimated Cost ($) | Sum of Actual Cost ($) | Sum of EAC | Sum of VAC
Customer Handover | 1600 | 1600 | 2880 | -1280
Design Finalization | 2520 | 720 | 2880 | -360
Final Finishes | 1120 | 800 | 1440 | -320
Foundation Completion | 2000 | 1200 | 3600 | -1600
Planning Approval | 2400 | 1200 | 1200 | 1200
Structural Inspection | 1200 | 1200 | 2000 | -800
Grand Total | 10840 | 6720 | 14000 | -3160

## Dashboard2 (hidden)
Sum of EAC | Sum of Projected Revenue ($) | Sum of Projected Profit ($)
14000 | 14092 | 92

## Live Plan (Editable)
Project ID | Project Name | Milestone | Phase | Start Date | End Date | Duration (Days) | Planned Resources | Owner | Role | Daily Rate ($) | Estimated Cost ($) | % Complete | Status | Days Passed | Actual Cost ($) | Budget Variance ($) | Cost Variance($) | Schedule Variance | Projected End Date | Estimated Time to Complete (Days) | Estimated Cost to Complete ($) | EAC | VAC | Projected Revenue ($) | Projected Profit ($) | Profitable/Loss | Risks | Scope/other Change Request
1 | ABC | Planning Approval | Phase 1 | 2025-06-17 | 2025-06-20 | 4 | 3 | Alice, Neal | Project Manager | 200 | 2400 | 100 | Completed | 2 | 1200 | 1200 | 1200 | 1200 | 2025-06-21 | 0 | 0 | 1200 | 1200 | 3120 | 1920 | Profitable | risk 1, umportant, extremely important | something 1, something 2
1 | ABC | Design Finalization | Phase 2 | 2025-06-22 | 2025-06-28 | 7 | 2 | Bob, Partha | Architect | 180 | 2520 | 10 | In Progress | 2 | 720 | 1800 | -468 | -468 | 2025-08-31 | 6 | 2160 | 2880 | -360 | 3276 | 396 | Profitable
1 | ABC | Foundation Completion | Phase 3 | 2025-06-27 | 2025-07-01 | 5 | 3 | Alice | Project Manager | 200 | 2000 | 25 | In Progress | 2 | 1200 | 800 | -700 | -300 | 2025-07-17 | 4 | 2400 | 3600 | -1600 | 2600 | -1000 | Loss
1 | ABC | Structural Inspection | Phase 4 | 2025-07-02 | 2025-07-04 | 3 | 2 | Alice | Project Manager | 200 | 1200 | 25 | In Progress | 3 | 1200 | 0 | -900 | -900 | 2025-07-14 | 2 | 800 | 2000 | -800 | 1560 | -440 | Loss
1 | ABC | Final Finishes | Phase 5 | 2025-07-07 | 2025-07-13 | 7 | 1 | Diana | QA Inspector | 160 | 1120 | 50 | In Progress | 5 | 800 | 320 | -240 | -240 | 2025-07-21 | 4 | 640 | 1440 | -320 | 1456 | 16 | Profitable
1 | ABC | Customer Handover | Phase 6 | 2025-07-12 | 2025-07-16 | 5 | 2 | Diana | QA Inspector | 160 | 1600 | 25 | In Progress | 5 | 1600 | 0 | -1200 | -1200 | 2025-08-01 | 4 | 1280 | 2880 | -1280 | 2080 | -800 | Loss
|  | Project Summary |  |  |  | 31 | 13 |  |  |  | 10840 | 39.1667 |  | 19 | 6720 | 4120 | -2308 | -1908 |  |  | 7280 | 14000 | -3160 | 14092 | 92 | 3
2 | ABC | Planning Approval | Phase 1 | 2025-06-17 | 2025-06-20 | 4 | 3 | Alice, Neal | Project Manager | 200 | 2400 | 100 | Completed | 2 | 1200 | 1200 | 1200 | 1200 | 2025-06-21 | 0 | 0 | 1200 | 1200 | 3120 | 1920 | Profitable | risk 1, umportant, extremely important | something 1, something 2
2 | ABC | Design Finalization | Phase 2 | 2025-06-22 | 2025-06-28 | 7 | 2 | Bob, Partha | Architect | 180 | 2520 | 10 | In Progress | 2 | 720 | 1800 | -468 | -468 | 2025-08-31 | 6 | 2160 | 2880 | -360 | 3276 | 396 | Profitable
2 | ABC | Foundation Completion | Phase 3 | 2025-06-27 | 2025-07-01 | 5 | 3 | Alice | Project Manager | 200 | 2000 | 25 | In Progress | 2 | 1200 | 800 | -700 | -300 | 2025-07-17 | 4 | 2400 | 3600 | -1600 | 2600 | -1000 | Loss
2 | ABC | Structural Inspection | Phase 4 | 2025-07-02 | 2025-07-04 | 3 | 2 | Alice | Project Manager | 200 | 1200 | 25 | In Progress | 3 | 1200 | 0 | -900 | -900 | 2025-07-14 | 2 | 800 | 2000 | -800 | 1560 | -440 | Loss
2 | ABC | Final Finishes | Phase 5 | 2025-07-07 | 2025-07-13 | 7 | 1 | Diana | QA Inspector | 160 | 1120 | 50 | In Progress | 5 | 800 | 320 | -240 | -240 | 2025-07-21 | 4 | 640 | 1440 | -320 | 1456 | 16 | Profitable
2 | ABC | Customer Handover | Phase 6 | 2025-07-12 | 2025-07-16 | 5 | 2 | Diana | QA Inspector | 160 | 1600 | 25 | In Progress | 5 | 1600 | 0 | -1200 | -1200 | 2025-08-01 | 4 | 1280 | 2880 | -1280 | 2080 | -800 | Loss
Formulas:
Projected End Date = IF(M2>0, [Start Date] + ([Duration (Days)] / (M2 / 100)), "")
Projected End Date = IF(AND(ISNUMBER([Start Date]), M7>0), [Start Date] + ([Duration (Days)] / (M7 / 100)), "")

## Dashboard (hidden)
Row Labels | Sum of Formula (Referring to Live Plan (Editable))
Baseline Profit ($) | 3252
Baseline Profit (%) | 0.23077
Expected Profit (%) | 0.0065285
Expected Profit at Completion ($) | 92
Overall Profit /Loss | 0.0065285
Profit Gap vs. Baseline ($) | -3160
Profit Gap vs. Baseline (%) | -0.97171
Total Projected Profit ($) | 92
Grand Total | 275.2721

## Sheet6 (hidden)
Row Labels | Sum of Formula (Referring to Live Plan (Editable))
# Loss-Making Milestones | 3
# Profitable Milestones | 3
% Milestones Completed | 0.16667
Average % Completion | 39.1667
Total Actual Cost ($) | 6720
Total Budget Variance ($) | 4120
Total Cost Variance ($) | -2308
Total Days Passed | 19
Total Duration (Days) | 31
Total EAC | 14000
Total Estimated Cost to Complete | 7280
Total Planned Resources | 13
Total Projected Profit ($) | 92
Total Projected Revenue ($) | 14092 | Row Labels | Sum of Formula (Referring to Live Plan (Editable))
Total Schedule Variance (Days) | -1908 | Total EAC | 14000
Total VAC | -3160 | Total Projected Profit ($) | 92
Grand Total | 39036.3333 | Total Projected Revenue ($) | 14092
|  | Grand Total | 28184

## KPI s
Project ID | Metric | Formula (Referring to Live Plan (Editable))
1 | Total Duration (Days) | 31 | =SUM('Live Plan (Editable)'!G2:G7)
1 | Total ETC (Days) | 20 | =SUM('Live Plan (Editable)'!U2:U7)
1 | New Total Duration (Days) | 51 | =SUM('Live Plan (Editable)'!G2:G7) + SUM('Live Plan (Editable)'!U2:U7)
1 | Schedule Extension (Days); | 20 | =SUM('Live Plan (Editable)'!U2:U7)
1 | Total Planned Resources | 13 | =SUM('Live Plan (Editable)'!H2:H7)
1 | Average % Completion | 39.1667 | =AVERAGE('Live Plan (Editable)'!M2:M7)
1 | Total Days Passed | 19 | =SUM('Live Plan (Editable)'!O2:O7)
1 | Total Actual Cost ($) | 6720 | =SUM('Live Plan (Editable)'!P2:P7)
1 | Total Budget Variance ($) | 4120 | =SUM('Live Plan (Editable)'!Q2:Q7)
1 | Total Cost Variance ($) | -2308 | =SUM('Live Plan (Editable)'!R2:R7)
1 | Total Schedule Variance (Days) | -1908 | =SUM('Live Plan (Editable)'!S2:S7)
1 | Total Estimated Cost to Complete | 7280 | =SUM('Live Plan (Editable)'!V2:V7)
1 | Total EAC | 14000 | =SUM('Live Plan (Editable)'!W2:W7)
1 | Total VAC | -3160 | =SUM('Live Plan (Editable)'!X2:X7)
1 | Total Projected Revenue ($) | 14092 | =SUM('Live Plan (Editable)'!Y2:Y7)
1 | Total Projected Profit ($) | 92 | =SUM('Live Plan (Editable)'!Z2:Z7)
1 | # Profitable Milestones | 3 | =COUNTIF('Live Plan (Editable)'!AA2:AA7, "Profitable")
1 | # Loss-Making Milestones | 3 | =COUNTIF('Live Plan (Editable)'!AA2:AA7, "Loss")
1 | % Milestones Completed | 16.67% | =COUNTIF('Live Plan (Editable)'!N2:N7,"Completed") / COUNTA('Live Plan (Editable)'!C2:C7)
1 | Total Estimated Cost ($) | 10840 | =SUM('Live Plan (Editable)'!L2:L7)
1 | Overall Status | In Progress | =IF( COUNTIF( 'Live Plan (Editable)'!N2:N7, "Completed" ) = COUNTA( 'Live Plan (Editable)'!C2:C7 ), "Completed", "In Progress" )
1 | Initial Finish Date | 2025-07-16 | =MAX('Live Plan (Editable)'!F2:F7)
1 | Projected Finish Date | 2025-08-31 | =MAX('Live Plan (Editable)'!T2:T7)
1 | Total Risks | 3 | =SUMPRODUCT( (LEN('Live Plan (Editable)'!AB2:AB7) - LEN(SUBSTITUTE('Live Plan (Editable)'!AB2:AB7, ",", ""))) + (LEN('Live Plan (Editable)'!AB2:AB7)>0) )
1 | Total Scope Changes | 2 | =SUMPRODUCT( (LEN('Live Plan (Editable)'!AC2:AC7) - LEN(SUBSTITUTE('Live Plan (Editable)'!AC2:AC7, ",", ""))) + (LEN('Live Plan (Editable)'!AC2:AC7)>0) )
1 | Budget Spent (%) | 61.99% | =SUM('Live Plan (Editable)'!P2:P7) / SUM('Live Plan (Editable)'!L2:L7)
1 | Budget Remaining ($) | 4120 | =SUM('Live Plan (Editable)'!L2:L7) - SUM('Live Plan (Editable)'!P2:P7)
1 | Overall Profit /Loss | 0.6529% | =SUM('Live Plan (Editable)'!Z2:Z7) / SUM('Live Plan (Editable)'!Y2:Y7)
1 | Baseline Profit ($) | 3252 | =SUM('Live Plan (Editable)'!Y2:Y7) - SUM('Live Plan (Editable)'!L2:L7)
1 | Expected Profit at Completion ($) | 92 | =SUM('Live Plan (Editable)'!Y2:Y7) - SUM('Live Plan (Editable)'!W2:W7)
1 | Profit Gap vs. Baseline ($) | -3160 | =(SUM('Live Plan (Editable)'!Y2:Y7) - SUM('Live Plan (Editable)'!W2:W7)) - (SUM('Live Plan (Editable)'!Y2:Y7) - SUM('Live Plan (Editable)'!L2:L7))
1 | Baseline Profit (%) | 23.08% | =( SUM('Live Plan (Editable)'!Y2:Y7) - SUM('Live Plan (Editable)'!L2:L7) ) / SUM('Live Plan (Editable)'!Y2:Y7)
1 | Expected Profit (%) | 0.6529% | =( SUM('Live Plan (Editable)'!Y2:Y7) - SUM('Live Plan (Editable)'!W2:W7) ) / SUM('Live Plan (Editable)'!Y2:Y7)
1 | Profit Gap vs. Baseline (%) | -97.17% | =( (SUM('Live Plan (Editable)'!L2:L7) - SUM('Live Plan (Editable)'!W2:W7)) / (SUM('Live Plan (Editable)'!Y2:Y7) - SUM('Live Plan (Editable)'!L2:L7)) )
1 | Profitable Milestone | Planning Approval, Design Finalization, Final Finishes | =TEXTJOIN(", ", TRUE, FILTER( 'Live Plan (Editable)'!C2:C7, 'Live Plan (Editable)'!AA2:AA7 = "Profitable" ) )
1 | Loss making Milestones | Foundation Completion, Structural Inspection, Customer Handover | =TEXTJOIN(", ", TRUE, FILTER( 'Live Plan (Editable)'!C2:C7, 'Live Plan (Editable)'!AA2:AA7 = "Loss" ) )
1 | Project Owners | Alice, Neal, Bob, Partha, Alice, Diana | =TEXTJOIN(", ", TRUE, UNIQUE( FILTER( 'Live Plan (Editable)'!I2:I1000, 'Live Plan (Editable)'!I2:I1000 <> "" ) ) )

## Sheet7 (hidden)
Total Duration (Days)
Total ETC (Days)
New Total Duration (Days)
Schedule Extension (Days);
Total Planned Resources
Average % Completion
Total Days Passed
Total Actual Cost ($)
Total Budget Variance ($)
Total Cost Variance ($)
Total Schedule Variance (Days)
Total Estimated Cost to Complete
Total EAC
Total VAC
Total Projected Revenue ($)
Total Projected Profit ($)
# Profitable Milestones
# Loss-Making Milestones
% Milestones Completed
Total Estimated Cost ($)
Overall Status
Initial Finish Date
Projected Finish Date
Total Risks
Total Scope Changes
Budget Spent (%)
Budget Remaining ($)
Overall Profit /Loss
Baseline Profit ($)
Expected Profit at Completion ($)
Profit Gap vs. Baseline ($)
Baseline Profit (%)
Expected Profit (%)
Profit Gap vs. Baseline (%)
Profitable Milestone
Loss making Milestones
Project Owners

## Sheet9 (hidden)
Row Labels
<00-01-1900
1900
2025
Grand Total

## Sheet10 (hidden)
Row Labels | Sum of Total Actual Cost ($) | Sum of Total Duration (Days)2 | Sum of Total ETC (Days) | Sum of New Total Duration (Days) | Sum of Schedule Extension (Days); | Sum of Total Planned Resources | Sum of Total Days Passed
1 | 6720 | 31 | 20 | 51 | 20 | 13 | 19
39.1667 | 6720 | 31 | 20 | 51 | 20 | 13 | 19
(blank) | 0 | 0 | 0 | 0 | 0 | 0 | 0
#DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0
(blank) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 6720 | 31 | 20 | 51 | 20 | 13 | 19

## Pivoting Chart Test examples
Project ID | 2
Sum of Total Duration (Days) | Sum of Total ETC (Days) | Sum of New Total Duration (Days) | Sum of Schedule Extension (Days);
31 | 20 | 51 | 20
|  |  |  | Project ID | 1
|  |  |  | Project Name | (All)
|  |  |  | Sum of Total EAC | Sum of Total Estimated Cost ($) | Sum of Total Budget Variance ($) | Sum of Total Projected Profit ($)
|  |  |  | 14000 | 10840 | 4120 | 92
[5 empty] | Project ID | 1
[5 empty] | Sum of Total Estimated Cost ($) | Sum of Total Actual Cost ($) | Sum of Budget Remaining ($)
[5 empty] | 10840 | 6720 | 4120
[7 empty] | Row Labels | Sum of Total Duration (Days) | Sum of New Total Duration (Days) | Sum of Schedule Extension (Days);
[7 empty] | 1 | 31 | 51 | 20
[7 empty] | 2025-06-17 | 31 | 51 | 20
[7 empty] | 2025-07-16 | 31 | 51 | 20
[7 empty] | 2025-08-31 | 31 | 51 | 20
[7 empty] | Grand Total | 31 | 51 | 20

## Dashboard Final Data
Total Duration (Days) | Project ID | Project Name | Total Duration (Days) | Total ETC (Days) | New Total Duration (Days) | Schedule Extension (Days); | Total Planned Resources | Average % Completion | Total Days Passed | Total Actual Cost ($) | Total Budget Variance ($) | Total Cost Variance ($) | Total Schedule Variance (Days) | Total Estimated Cost to Complete | Total EAC | Total VAC | Total Projected Revenue ($) | Total Projected Profit ($) | # Profitable Milestones | # Loss-Making Milestones | % Milestones Completed | Total Estimated Cost ($) | Overall Status | Initial Finish Date | Projected Finish Date | Total Risks | Total Scope Changes | Budget Spent (%) | Budget Remaining ($) | Overall Profit /Loss | Baseline Profit ($) | Expected Profit at Completion ($) | Profit Gap vs. Baseline ($) | Baseline Profit (%) | Expected Profit (%) | Profit Gap vs. Baseline (%) | Profitable Milestone | Loss making Milestones | Project Owners | Start date | End date | Projected End Date
Total ETC (Days) | 1 | #N/A | 31 | 20 | 51 | 20 | 13 | 39.1667 | 19 | 6720 | 4120 | -2308 | -1908 | 7280 | 14000 | -3160 | 14092 | 92 | 3 | 3 | 0.16667 | 10840 | In Progress | 2025-07-16 | 2025-08-31 | 3 | 2 | 0.61993 | 4120 | 0.0065285 | 3252 | 92 | -3160 | 0.23077 | 0.0065285 | -0.97171 | Planning Approval, Design Finalization, Final Finishes | Foundation Completion, Structural Inspection, Customer Handover | Alice, Neal, Bob, Partha, Alice, Diana | 2025-06-17 | 2025-07-16 | 2025-08-31
New Total Duration (Days) | 2 | #N/A | 31 | 20 | 51 | 20 | 13 | 39.1667 | 19 | 6720 |  | -2308 | -1908 | 7280 | 14000 | -3160 | 14092 | 92 | 3 | 3 | 0.16667 | 10840 | In Progress | 2025-07-16 | 2025-08-31 | 3 | 2 | 0.61993 | 4120 | 0.0065285 | 3252 | 92 | -3160 | 0.23077 | 0.0065285 | -0.97171 | Planning Approval, Design Finalization, Final Finishes | Foundation Completion, Structural Inspection, Customer Handover | Alice, Neal, Bob, Partha, Alice, Diana | 2025-06-17 | 2025-07-16 | 2025-08-31
Schedule Extension (Days); |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Planned Resources |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Average % Completion |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Days Passed |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Actual Cost ($) |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Budget Variance ($) |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Cost Variance ($) |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Schedule Variance (Days) |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Estimated Cost to Complete |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total EAC |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total VAC |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Projected Revenue ($) |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Projected Profit ($) |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
# Profitable Milestones |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
# Loss-Making Milestones |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
% Milestones Completed |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Estimated Cost ($) |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Overall Status |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Initial Finish Date |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Projected Finish Date |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Risks |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Total Scope Changes |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Budget Spent (%) |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Budget Remaining ($) |  | #N/A | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Overall Profit /Loss |  | #N/A | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Baseline Profit ($) |  | #N/A | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Expected Profit at Completion ($) |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Profit Gap vs. Baseline ($) |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | Completed | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Baseline Profit (%) |  |  | 0 | [10 empty] | 0 | 0 | [9 empty] | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Expected Profit (%) |  |  | 0 | [10 empty] | 0 | 0 | [9 empty] | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Profit Gap vs. Baseline (%) |  |  | 0 | [10 empty] | 0 | 0 | [9 empty] | 0 |  |  |  | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Profitable Milestone |  |  | 0 | [10 empty] | 0 | 0 | [9 empty] | 0 |  |  |  | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Loss making Milestones |  |  | 0 | [10 empty] | 0 | [10 empty] | 0 |  |  |  | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0
Project Owners | [24 empty] | 0 |  |  |  | 0 | [9 empty] | #VALUE!
Formulas:
Initial Finish Date = MAXIFS('Live Plan (Editable)'!F:F,'Live Plan (Editable)'!A:A,[Project ID])
Projected Finish Date = MAXIFS( 'Live Plan (Editable)'!$T:$T, 'Live Plan (Editable)'!$A:$A, [Project ID] )
Start date = MINIFS('Live Plan (Editable)'!$E:$E, 'Live Plan (Editable)'!$A:$A, [Project ID])
End date = MAXIFS( 'Live Plan (Editable)'!$F:$F, 'Live Plan (Editable)'!$A:$A, [Project ID] )
Projected End Date = MAXIFS( 'Live Plan (Editable)'!$T:$T, 'Live Plan (Editable)'!$A:$A, [Project ID] )